## Sheet1
Project	Task	Added	Completed	Description	Notes
ROSV	Scope	01/01/13	01/02/13	Write Scope of works
ROSV	Overview	01/01/13	01/02/13	Write Project overview
ROSV	Mech drawings	01/01/13		Basic mech drawings of the frame.
ROSV	Notes	01/01/13		start detailing what I have learnt.
ROSV	Pictures/Photos	01/01/13		pics of hardware & frame
ROSV	Scripting	01/01/13		writing scripts to start/stop camera service.
ROSV	Scripting	01/01/13		Write scripts to monitor process' performance.
ROSV	Documentation	01/01/13		Draw block diagram of hardware
ROSV	Documentation	01/01/13		Draw deployment diagram
ROSV	Documentation	01/01/13		Document protocol between Control and Console.
ROSV	Documentation	01/01/13		Draw basic system flowchart

PWM Controller	Firmware	01/01/13		Add coms timeout module
PWM Controller	Firmware	01/01/13		Add PWM driver code
PWM Controller	Firmware	01/01/13		Add Current monitor code
PWM Controller	Firmware	01/01/13		Add RTC Clock code
PWM Controller	Daemon & test prog	01/01/13	01/02/13	Document class diagram: daemon
PWM Controller	Daemon & test prog	01/01/13	01/02/13	Flowchart basic operations: Daemon
PWM Controller	Daemon & test prog			write daemon
Daemon & test prog				Write test program

INS Controller	Firmware	01/01/13		Draw class diagram
INS Controller	Firmware	01/01/13		Draw Flowcharts
INS Controller	Firmware	01/01/13		Write/Test basic framework.
INS Controller	Firmware	01/01/13		Add code to read temp sensor.
INS Controller	Firmware	01/01/13		Add code to read Accel/Gyro readings.
INS Controller	Firmware	01/01/13		Add filtering algorithm to calculate velocity.
INS Controller	Firmware	01/01/13		Add filtering algorithm to calculate position.
INS Controller	Daemon & test prog	01/01/13		Draw class diagram
INS Controller	Daemon & test prog	01/01/13		Flowchart basic operations: Daemon

ROSV_Control	Documentation	01/01/13		Draw class diagram
ROSV_Control	Documentation	01/01/13		Draw flowchart explaining basic operations

ROSV_Console	Documentation	01/01/13		Draw class diagram
ROSV_Console	Documentation	01/01/13		Draw basic UI
ROSV_Console	Documentation	01/01/13		Draw flowchart explaining basic operations